Table of Contents

# Dedicated to Enterprise Migration

## Complete Step-by-Step Guide

Confluent Cloud Platform Migration

## Agenda

- Migration Overview

- Step 1: Discovery & Sizing

- Step 2: Provision Enterprise Cluster

- Step 3: Establish Cluster Linking

- Step 4: Migrate Applications (Pilot)

- Step 5: Full Application Migration

- Step 6: Validation & Monitoring

- Step 7: Decommission Dedicated

- Timeline & Resource Requirements

- Risk Mitigation & Rollback

## Migration Overview

### The Big Picture

7-Step Migration Process: 1. ✅ Measure current usage 2. ✅ Build Enterprise cluster 3. ✅ Connect clusters (Cluster Linking) 4. ✅ Test with pilot application 5. ✅ Migrate all applications 6. ✅ Validate everything works 7. ✅ Cleanup and decommission

Duration: 4-11 weeks
Downtime: ZERO
Rollback: Available at any stage

## Migration Principles

### Zero-Downtime Guarantee

How we achieve zero downtime: - Dedicated cluster continues running - Enterprise cluster built in parallel - Cluster Linking syncs data in real-time - Applications migrate gradually - Rollback available until final cleanup

Key Technology: Cluster Linking - Real-time data synchronization - Automatic failover capability - Consumer offset preservation

## STEP 1: Discovery & Sizing

### Week 1-2

## Step 1.1: Gather Current Metrics

### What to Collect

From Confluent Cloud Console → Metrics:

| Metric | Purpose |
| --- | --- |
| Peak Ingress/Egress | Maximum throughput capacity needed |
| Average Ingress/Egress | Baseline capacity for sizing |
| Partition Count | Critical for Enterprise sizing |
| Storage (GB) | Retention costs |
| Current CKUs | Comparison baseline |
| Cluster Load | Utilization patterns |

Time Period: Last 90 days minimum

## Step 1.2: Analyze Workload Patterns

### Spike Analysis

Questions to Answer:

✅ Are there daily spikes? (Business hours vs. night)
✅ Are there weekly spikes? (Monday mornings, Friday EOD)
✅ How big are spikes? (2x? 5x? 10x average?)
✅ How long do spikes last? (Minutes? Hours?)

Example Analysis:

Normal traffic: 30 MB/sec ingress
Peak traffic: 90 MB/sec ingress (3x spike)
Spike frequency: Daily, 9 AM - 6 PM (9 hours/day)
Spike duration: 9 hours per day

Recommendation: Enterprise ideal (auto-scaling benefit)

## Step 1.3: Count Partitions

### Critical for Sizing!

Why Partitions Matter: - Dedicated: ~4,500 partitions per CKU - Enterprise: ~3,000 partitions per eCKU - Enterprise has 1,500 FEWER partitions per unit!

How to Count:

confluent kafka topic list --cluster <cluster-id>
# Sum all partition counts across topics

Example:

100 topics × average 20 partitions = 2,000 total partitions
Enterprise needs: 2,000 ÷ 3,000 = 0.67 eCKU (round up to 1)
But 99.99% SLA requires minimum 2 eCKU
Final: 2 eCKU baseline

## Step 1.4: Size Enterprise Cluster

### Sizing Formula

Calculate BOTH dimensions:

A. Throughput-Based:

eCKU needed = Average Ingress ÷ 50 MB/sec per eCKU
(or)
eCKU needed = Average Egress ÷ 150 MB/sec per eCKU

B. Partition-Based:

eCKU needed = Total Partitions ÷ 3,000 per eCKU

C. SLA Minimum:

99.9% SLA = 1 eCKU minimum
99.99% SLA = 2 eCKU minimum

Final Size = MAX(throughput, partitions, SLA minimum)

## Step 1.5: Cost Estimation

### Build Business Case

Use Confluent Pricing Calculator: - Input: Cloud provider, region, eCKU, SLA - Output: Monthly cost estimate

Example Calculation:

Enterprise Cost Estimate:
- 2 eCKU baseline @ 99.99%: $2,800/month
- Auto-scaling (estimated): $400/month
- Storage (100 GB): $10/month
- Networking: $150/month
─────────────────────────────
Total: $3,360/month

Current Dedicated: $4,500/month
Monthly Savings: $1,140 (25%)
Annual Savings: $13,680

## Step 1.6: Calculate ROI

### Include Overlap Costs

One-Time Migration Costs:

Overlap period (4 weeks paying for both):
- Dedicated: $4,500
- Enterprise: $3,360
─────────────────────────────
Total overlap: $7,860 one-time

Payback Calculation:

Payback = Overlap Cost ÷ Monthly Savings
        = $7,860 ÷ $1,140
        = 6.9 months

Year 1 Net Savings:
($1,140 × 12 months) - $7,860 = $5,820

## Step 1 Deliverables

### Documentation to Create

Migration Inventory Document: - Current cluster configuration - Application list (producers, consumers) - Connector inventory - Flink job inventory - Topic list with partition counts - Current monthly costs - Estimated Enterprise costs - ROI calculation

Stakeholder Presentation: - Business case for migration - Cost savings analysis - Timeline estimate - Risk assessment

## STEP 2: Provision Enterprise Cluster

### Week 2

## Step 2.1: Create Enterprise Cluster

### Using Confluent Cloud UI

Process: 1. Log into Confluent Cloud 2. Click “Add Cluster” 3. Select “Enterprise” type 4. Configure: - Cloud: AWS/Azure/GCP - Region: SAME as Dedicated - Availability: Multi-zone (99.99% SLA) - eCKU: Your calculated baseline 5. Launch cluster (15-30 min provisioning)

Critical: Choose SAME region as Dedicated for Cluster Linking!

## Step 2.2: Using Terraform (Recommended)

### Infrastructure as Code

Benefits: - Repeatable deployments - Version controlled - Automated provisioning - Easy to replicate across environments

Terraform Configuration:

resource "confluent_kafka_cluster" "enterprise" {
  display_name = "enterprise-prod"
  availability = "MULTI_ZONE"
  cloud        = "AWS"
  region       = "us-east-1"
  
  enterprise {
    ecku = 2
  }
  
  environment {
    id = confluent_environment.prod.id
  }
}

## Step 2.3: Set Up Private Networking

### Private Link Configuration

Why Private Link: - Secure private connectivity - No internet exposure - Reduced networking costs (especially with PNI on AWS) - AWS/Azure/GCP best practice

Steps: 1. Create Gateway in Confluent Cloud 2. Create Access Point 3. Create VPC Endpoint in your cloud provider 4. Accept connection in Confluent 5. Configure DNS (private hosted zones)

## Private Link Architecture

### Enterprise Networking Model

Your VPC
   │
   ├─ Private Link Connection
   │
   └─ Ingress Gateway
       │
       ├─ Access Point (Kafka)
       │   └─ pkc-xxxxx.region.aws.confluent.cloud:9092
       │
       ├─ Access Point (Schema Registry)
       │   └─ psrc-xxxxx.region.aws.confluent.cloud
       │
       └─ Access Point (Flink)
           └─ flink-xxxxx.region.aws.confluent.cloud

Note: Each service has dedicated endpoint (different from Dedicated)

## Step 2.4: Configure DNS

### Critical for Application Connectivity

Create Private Hosted Zone:

AWS Route 53 Example:

1. Create hosted zone for confluent.cloud
2. Associate with your VPC
3. Add A records for each endpoint:
   - Kafka endpoint
   - Schema Registry endpoint
   - Flink endpoint (if used)

Test Resolution:

nslookup pkc-xxxxx.us-east-1.aws.confluent.cloud
# Should resolve to private IP (10.x.x.x)

## Step 2.5: Create Service Accounts

### Security Configuration

Option 1: Reuse Existing (Recommended)

# Grant existing service accounts access to Enterprise
confluent kafka acl create \
  --cluster <enterprise-cluster-id> \
  --allow \
  --service-account <existing-sa-id> \
  --operation WRITE --operation READ \
  --topic '*' \
  --consumer-group '*'

Option 2: Create New

# Create new service account for Enterprise
confluent iam service-account create app-producer \
  --description "Producer for Enterprise"

# Generate API key
confluent api-key create \
  --service-account <sa-id> \
  --resource <enterprise-cluster-id>

## Step 2.6: Configure Schema Registry

### Schema Management Setup

Enable Schema Registry:

confluent schema-registry cluster enable \
  --cloud aws \
  --geo us \
  --environment <env-id>

Get Endpoint:

Output: https://psrc-xxxxx.us-east-1.aws.confluent.cloud

Create API Key:

confluent api-key create \
  --resource <schema-registry-id> \
  --service-account <sa-id>

## Step 2.7: Validate Enterprise Cluster

### Connectivity Testing

Test Kafka Connection:

kcat -b pkc-xxxxx.us-east-1.aws.confluent.cloud:9092 \
  -X security.protocol=SASL_SSL \
  -X sasl.mechanisms=PLAIN \
  -X sasl.username=<api-key> \
  -X sasl.password=<api-secret> \
  -L

Create Test Topic:

confluent kafka topic create test-migration \
  --cluster <enterprise-cluster-id> \
  --partitions 3

Produce Test Message:

echo "Migration test successful" | kcat ... -t test-migration -P

Consume Test Message:

kcat ... -t test-migration -C

✅ If message received → Cluster ready!

## Step 2 Deliverables

### What You Should Have

Infrastructure: - ✅ Enterprise cluster running - ✅ Private Link configured and tested - ✅ DNS configured and validated - ✅ Service accounts created with permissions - ✅ Schema Registry enabled

Documentation: - Enterprise cluster details (ID, endpoints) - Service account credentials (securely stored) - Network configuration (VPC endpoints, DNS zones) - Terraform code (if used)

Validation: - Connectivity test results - Test message produce/consume successful

## STEP 3: Establish Cluster Linking

### Week 2-3

## Step 3.1: Understand Cluster Linking

### The Magic Behind Zero-Downtime

What is Cluster Linking: - Real-time data synchronization between clusters - Native Kafka replication protocol - Preserves topic data, schemas, and consumer offsets - Enables zero-downtime migration

How It Works:

Dedicated Cluster (Source)
   │
   │ ← Cluster Link (continuous sync)
   │
   ↓
Enterprise Cluster (Destination)
   └─ Mirror Topics (read-only copies)

## Step 3.2: Create Cluster Link

### Configuration

Important: Create link FROM Enterprise (destination) TO Dedicated (source)

Via Confluent Cloud UI: 1. Navigate to Enterprise Cluster → Cluster Linking 2. Click “Create cluster link” 3. Source cluster: Select Dedicated 4. Link name: dedicated-to-enterprise 5. Enable consumer offset sync ✅ 6. Select topics to mirror (or “All topics”)

Via CLI:

confluent kafka link create dedicated-to-enterprise \
  --source-cluster <dedicated-cluster-id> \
  --destination-cluster <enterprise-cluster-id> \
  --source-api-key <dedicated-key> \
  --source-api-secret <dedicated-secret> \
  --config consumer.offset.sync.enable=true

## Step 3.3: Create Mirror Topics

### Topic Synchronization

Mirror All Topics:

# Get topic list from Dedicated
confluent kafka topic list --cluster <dedicated-id>

# Create mirrors on Enterprise
confluent kafka topic list --cluster <dedicated-id> | \
  while read topic; do
    confluent kafka mirror create $topic \
      --cluster <enterprise-cluster-id> \
      --link dedicated-to-enterprise \
      --source-topic $topic
  done

Or Mirror Specific Topics:

confluent kafka mirror create orders \
  --cluster <enterprise-cluster-id> \
  --link dedicated-to-enterprise \
  --source-topic orders

## Step 3.4: Monitor Cluster Link Lag

### Key Metric: Mirror Lag

What is Mirror Lag: - Number of messages Enterprise is behind Dedicated - Goal: Lag → 0 before migrating applications

Check Lag:

confluent kafka link describe dedicated-to-enterprise \
  --cluster <enterprise-cluster-id>

confluent kafka mirror list \
  --cluster <enterprise-cluster-id> \
  --link dedicated-to-enterprise

Typical Backfill Timeline: - Small cluster (100 GB): 1-4 hours - Medium cluster (1 TB): 4-12 hours - Large cluster (10+ TB): 1-3 days

Monitor in UI: Enterprise Cluster → Cluster Linking → View lag metric

## Cluster Link Status Progression

### What to Expect

Phase 1: Initial Backfill (Hours to Days)

Mirror Lag: 5,000,000 messages
State: ACTIVE
Status: Syncing historical data

Phase 2: Catching Up

Mirror Lag: 500,000 messages (decreasing)
State: ACTIVE
Status: Almost synced

Phase 3: Fully Synced (Ready!)

Mirror Lag: 0-100 messages (near zero)
State: ACTIVE
Status: Ready for migration ✅

Only proceed to Step 4 when lag is near zero!

## Step 3.5: Verify Consumer Offset Sync

### Critical for Seamless Cutover

Why Consumer Offsets Matter: - Tell consumers “where they left off reading” - Prevent duplicate processing or data loss - Enable resumption on Enterprise from exact position

Check Offset Sync:

# List consumer groups on Dedicated
confluent kafka consumer group list --cluster <dedicated-id>

# Verify offsets synced to Enterprise
confluent kafka consumer group describe payment-processor \
  --cluster <enterprise-cluster-id>

Expected Output:

GROUP            TOPIC      PARTITION  OFFSET
payment-processor orders    0          125,430
payment-processor orders    1          124,980
payment-processor orders    2          125,100

✅ If offsets present on Enterprise → Consumers can resume seamlessly!

## Step 3 Deliverables

### What You Should Have

Cluster Link: - ✅ Link created and ACTIVE - ✅ All topics mirrored - ✅ Mirror lag near zero - ✅ Consumer offsets synced

Monitoring: - Dashboard showing mirror lag trends - Alerts configured for link failures - Regular lag checks documented

Readiness: - Enterprise cluster has complete copy of Dedicated data - Ready to begin application migration

## STEP 4: Pilot Migration

### Week 3 (1-3 days)

## Step 4.1: Select Pilot Application

### Choosing the Right Test Case

Ideal Pilot Characteristics:

✅ Non-critical - Low business impact if issues occur
✅ Simple - Minimal dependencies, straightforward logic
✅ Representative - Similar to other apps (validates process)
✅ Observable - Easy to monitor (good metrics, clear logs)
✅ Small scale - Limited traffic volume

Good Examples: - Analytics consumer reading user events - Internal monitoring dashboard - Dev/test application

Bad Examples: - Payment processing (too critical!) - Complex multi-service app (too many dependencies) - Legacy app with poor documentation

## Step 4.2: Stop Application on Dedicated

### Graceful Shutdown

For Consumer Applications:

# SSH to application server
ssh app-server-01

# Stop service gracefully
sudo systemctl stop analytics-consumer

# Verify stopped
sudo systemctl status analytics-consumer

For Containerized Apps (Kubernetes):

kubectl scale deployment analytics-consumer --replicas=0

# Verify pods terminated
kubectl get pods -l app=analytics-consumer

Important: Don’t stop producers yet! Only consumers in pilot.

## Step 4.3: Update Application Configuration

### Configuration Changes Required

OLD Configuration (Dedicated):

# application.properties
bootstrap.servers=pkc-old.us-east-1.aws.confluent.cloud:9092
security.protocol=SASL_SSL
sasl.mechanism=PLAIN
sasl.username=DEDICATED_API_KEY
sasl.password=DEDICATED_API_SECRET

schema.registry.url=https://psrc-old.us-east-1.aws.confluent.cloud
schema.registry.basic.auth.user.info=SR_KEY:SR_SECRET

group.id=analytics-consumer-group

NEW Configuration (Enterprise):

# application.properties
bootstrap.servers=pkc-xxxxx.us-east-1.aws.confluent.cloud:9092  ← Changed
security.protocol=SASL_SSL
sasl.mechanism=PLAIN
sasl.username=ENTERPRISE_API_KEY                                ← Changed
sasl.password=ENTERPRISE_API_SECRET                             ← Changed

schema.registry.url=https://psrc-xxxxx.us-east-1.aws.confluent.cloud  ← Changed
schema.registry.basic.auth.user.info=SR_KEY:SR_SECRET

group.id=analytics-consumer-group  ← SAME (important!)

## Configuration Update Methods

### How to Update Configs

Method 1: Configuration Files

# Edit application.properties
vi /etc/analytics-consumer/application.properties
# Update endpoints and credentials

Method 2: Environment Variables

# Update environment file
vi /etc/default/analytics-consumer

KAFKA_BOOTSTRAP_SERVERS=pkc-xxxxx.us-east-1.aws.confluent.cloud:9092
KAFKA_API_KEY=<enterprise-key>
KAFKA_API_SECRET=<enterprise-secret>

Method 3: Secrets Manager (Recommended)

# AWS Secrets Manager example
aws secretsmanager update-secret \
  --secret-id analytics-consumer/kafka \
  --secret-string '{
    "bootstrap": "pkc-xxxxx.us-east-1.aws.confluent.cloud:9092",
    "api_key": "<enterprise-key>",
    "api_secret": "<enterprise-secret>"
  }'

## Step 4.4: Start Application on Enterprise

### Launch and Monitor

Start Application:

# Start service
sudo systemctl start analytics-consumer

# Check status
sudo systemctl status analytics-consumer

Watch Logs Carefully:

# Tail application logs
sudo journalctl -u analytics-consumer -f

# Look for:
✅ "Successfully connected to Kafka"
✅ "Subscribed to topics: [user-events]"
✅ "Consumer group rebalanced"
✅ "Fetching records from partition..."

❌ "Connection refused"
❌ "Authentication failed"
❌ "Topic not found"

## Step 4.5: Validate Pilot Success

### Multi-Layer Validation

Level 1: Technical Validation

# Check consumer group lag on Enterprise
confluent kafka consumer group describe analytics-consumer-group \
  --cluster <enterprise-cluster-id>

Expected Output:
TOPIC        PARTITION  CURRENT-OFFSET  LAG
user-events  0          45,230          0      ← Lag should be 0
user-events  1          43,100          0
user-events  2          44,980          0

Level 2: Application Validation

# Check application metrics
curl http://localhost:8080/metrics | grep messages_processed

Expected: Counter increasing steadily

Level 3: Business Validation

# Verify business outcomes
- Dashboard shows data? ✅
- Alerts working? ✅
- Reports generating? ✅

## Pilot Validation Checklist

### Before Declaring Success

- Application started without errors

- Connected to Enterprise cluster (check logs)

- Consumer lag = 0 or decreasing

- No authentication/authorization errors

- Schema Registry working (if used)

- Application processing messages correctly

- Business metrics unchanged

- No duplicate message processing

- Downstream systems receiving data

- Ran for 24-48 hours without issues

- Stakeholders confirm “looks normal”

Only proceed to Step 5 when ALL checks pass!

## Step 4.6: Pilot Failure - Rollback

### If Pilot Has Issues

Rollback Procedure (Takes Minutes):

- Stop application on Enterprise

- sudo systemctl stop analytics-consumer

- Revert configuration to Dedicated

- # Restore old config
cp /etc/analytics-consumer/application.properties.backup \
   /etc/analytics-consumer/application.properties

- Restart on Dedicated

- sudo systemctl start analytics-consumer

- Verify working

- # Check consuming from Dedicated again
confluent kafka consumer group describe analytics-consumer-group \
  --cluster <dedicated-cluster-id>

Data Safety: Dedicated has all data - nothing lost!

## Pilot Troubleshooting Guide

### Common Issues and Fixes

Issue 1: Connection Refused

Error: "Failed to connect to pkc-xxxxx:9092"

Fixes:
✅ Check DNS resolution (nslookup endpoint)
✅ Verify Private Link endpoint created
✅ Check security groups allow port 9092
✅ Verify VPC routing to Private Link

Issue 2: Authentication Failed

Error: "SASL authentication failed"

Fixes:
✅ Verify API key is for Enterprise (not Dedicated)
✅ Check API key has correct permissions (ACLs)
✅ Ensure no typos in credentials
✅ Verify service account not deleted

Issue 3: Topic Not Found

Error: "Topic 'user-events' not found"

Fixes:
✅ Verify Cluster Link created mirror topic
✅ Check mirror topic name matches (case-sensitive)
✅ Ensure Cluster Link lag reached zero
✅ Verify topic permissions (ACLs)

## Step 4 Deliverables

### What You Should Have

Successful Pilot: - ✅ One application migrated and validated - ✅ Rollback procedure tested (if issues occurred) - ✅ Configuration update process documented - ✅ Validation checklist completed

Documentation: - Pilot application migration runbook - Troubleshooting notes (issues encountered and fixes) - Configuration templates for other apps - Validation criteria for future migrations

Lessons Learned: - What worked well - What needed adjustment - Estimated time per application - Skills/tools needed

## STEP 5: Full Application Migration

### Week 3-6 (2-4 weeks)

## Step 5.1: Plan Migration Waves

### Phased Migration Strategy

Wave 1: Low-Risk Consumers (Week 3) - Analytics consumers - Monitoring/metrics consumers - Internal tooling - Dev/test applications - Risk Level: LOW

Wave 2: Business-Critical Consumers (Week 4) - Customer-facing applications - High-volume consumers - Real-time processing apps - Risk Level: MEDIUM

Wave 3: Producers (Week 5) - All producer applications - Only after consumers validated - Risk Level: MEDIUM-HIGH

Wave 4: Final Cutover (Week 5-6) - Promote mirror topics to writable - Cleanup and validation - Risk Level: HIGH

## Migration Waves - Visual Timeline

### 4-Week Execution Plan

Week 3: Wave 1 (Low-Risk Consumers)
├─ Day 1-2: Migrate analytics apps (5 apps)
├─ Day 3-4: Migrate monitoring apps (8 apps)
└─ Day 5: Validate, monitor

Week 4: Wave 2 (Critical Consumers)
├─ Day 1-2: Migrate customer apps (10 apps)
├─ Day 3-4: Migrate processing apps (7 apps)
└─ Day 5: Validate, monitor

Week 5: Wave 3 (Producers)
├─ Day 1: Stop all producers
├─ Day 2: Verify Cluster Link lag = 0
├─ Day 3: Promote topics to writable
├─ Day 4: Migrate producers (15 apps)
└─ Day 5: Validate end-to-end

Week 6: Final Validation
├─ Monitor all applications
├─ Verify business metrics
├─ Cost validation
└─ Stakeholder sign-off

## Step 5.2: Migrate Consumers

### Process for Each Consumer

Pre-Migration:

1. Identify all instances (servers, pods)
2. Backup current configuration
3. Update configuration for Enterprise
4. Update secrets/credentials
5. Schedule maintenance window (if needed)

Migration:

1. Stop consumer on Dedicated
2. Deploy updated config
3. Start consumer on Enterprise
4. Validate consuming (check lag)
5. Monitor for 24 hours

Post-Migration:

1. Confirm consumer lag stable
2. Verify business metrics
3. Document any issues
4. Mark application as "migrated"

## Step 5.3: Consumer Migration Checklist

### Per-Application Checklist

Application: [Name]

Pre-Migration: - [ ] Application owner notified - [ ] Configuration files updated - [ ] Credentials updated in secrets manager - [ ] Deployment scripts tested - [ ] Rollback plan documented - [ ] Monitoring alerts configured

Migration: - [ ] Application stopped on Dedicated - [ ] Configuration deployed - [ ] Application started on Enterprise - [ ] Logs reviewed (no errors) - [ ] Consumer lag checked (lag = 0)

Post-Migration: - [ ] 24-hour monitoring complete - [ ] Business metrics validated - [ ] Stakeholder confirmation received - [ ] Documentation updated

## Step 5.4: Promote Mirror Topics

### Making Topics Writable

When to Promote: - ✅ ALL consumers migrated and validated - ✅ Cluster Link lag = 0 - ✅ Ready to migrate producers

What “Promote” Means: - Mirror topics become independent (no longer read-only) - Topics accept writes on Enterprise - Topics stop syncing from Dedicated - WARNING: Dedicated and Enterprise will DIVERGE after this!

How to Promote:

# Promote single topic
confluent kafka mirror promote orders \
  --cluster <enterprise-cluster-id> \
  --link dedicated-to-enterprise

# Promote ALL topics
confluent kafka topic list --cluster <enterprise-cluster-id> | \
  while read topic; do
    confluent kafka mirror promote $topic \
      --cluster <enterprise-cluster-id> \
      --link dedicated-to-enterprise
  done

## Step 5.5: Migrate Producers

### Final Application Cutover

Pre-Migration:

1. Ensure ALL consumers migrated ✅
2. Ensure topics promoted ✅
3. Coordinate with all producer teams
4. Schedule coordinated maintenance window

Migration Process:

Step 1: Stop ALL Producers on Dedicated

# Stop all producer services
sudo systemctl stop order-service
sudo systemctl stop payment-service
sudo systemctl stop inventory-service
# ... all producers

Step 2: Verify Cluster Link Lag = 0

confluent kafka link describe dedicated-to-enterprise \
  --cluster <enterprise-cluster-id>

# Should show: Mirror Lag: 0 messages

## Producer Migration (Continued)

### Cutover Execution

Step 3: Promote Topics (if not done in Step 5.4)

# Make all topics writable on Enterprise
confluent kafka mirror promote <topic> ...

Step 4: Update Producer Configs

# OLD (Dedicated)
bootstrap.servers=pkc-old.us-east-1.aws.confluent.cloud:9092

# NEW (Enterprise)
bootstrap.servers=pkc-xxxxx.us-east-1.aws.confluent.cloud:9092

Step 5: Start Producers on Enterprise

sudo systemctl start order-service
sudo systemctl start payment-service
sudo systemctl start inventory-service

Step 6: Validate Producing

# Check messages arriving on topics
kcat -b <enterprise-bootstrap> \
  -X security.protocol=SASL_SSL \
  -t orders -C -e -q | wc -l

# Watch count increase over time

## Step 5.6: Parallel Migration Strategy

### For Large Application Counts

If you have 50+ applications:

Team-Based Parallelization:

Team A: Migrate their 15 apps (Week 3)
Team B: Migrate their 20 apps (Week 3)
Team C: Migrate their 18 apps (Week 4)
Team D: Migrate their 12 apps (Week 4)

Result: 65 apps migrated in 2 weeks (vs. 13 weeks sequential)

Automation: - Use configuration management (Ansible, Terraform) - Template configuration updates - Scripted deployment processes - Automated validation checks

Coordination: - Central migration team tracks progress - Daily standups to share learnings - Shared troubleshooting knowledge base - Slack channel for real-time support

## Step 5 Deliverables

### What You Should Have

Migrated Applications: - ✅ All consumers migrated and validated - ✅ All producers migrated and validated - ✅ Topics promoted to writable - ✅ Enterprise is primary production cluster

Status Tracking: - Migration status dashboard - Application inventory (migrated vs. pending) - Issues log and resolutions

Documentation: - Updated runbooks per application - Configuration templates - Troubleshooting guide - Lessons learned

Readiness: - Ready for validation period - Dedicated cluster running as backup - Rollback procedure documented

## STEP 6: Validation & Monitoring

### Week 6-11 (1-4 weeks)

## Step 6.1: Daily Monitoring

### What to Watch

Cluster Health Metrics:

✅ eCKU Utilization (40-80% healthy)
✅ Auto-scaling events (appropriate?)
✅ Disk usage (not growing unexpectedly)
✅ Network throughput (matching expectations)
✅ Partition distribution (balanced)
✅ No cluster alerts or errors

Application Health Metrics:

✅ Consumer lag = 0 or stable
✅ No errors in application logs
✅ Application throughput normal
✅ Response times within SLA
✅ No monitoring alerts triggered

Business Metrics:

✅ Orders processed = unchanged
✅ Payments processed = unchanged
✅ Events published = unchanged
✅ Revenue/conversions = unchanged

## Step 6.2: Auto-Scaling Validation

### Verify Auto-Scaling Working Correctly

Check Auto-Scaling Events:

Confluent Cloud UI → Enterprise Cluster → Activity Log

Look for:
✅ "Scaled up to 3 eCKU" (during traffic spike)
✅ "Scaled down to 2 eCKU" (after spike)

Validate Scaling Behavior:

During Spike:
- Time to scale up: < 2 minutes ✅
- Sufficient capacity added ✅
- No throttling or errors ✅

After Spike:
- Time to scale down: 5-15 minutes ✅
- Scales back to baseline ✅
- No performance degradation ✅

Review Scaling Costs:

Baseline: 2 eCKU @ $2,800/month
Auto-scaling: 400 hours @ $3/hour = $1,200
Total: $4,000/month

vs. Estimated: $3,360/month
Variance: +19% (investigate if large)

## Step 6.3: Cost Validation

### Verify Savings Realized

Compare Actual to Estimate:

Estimated Enterprise: $3,360/month
Actual Enterprise (prorated): 
  - 20 days usage: $2,240
  - Projected full month: $3,360 ✅

vs. Dedicated: $4,500/month
Actual Savings: $1,140/month (25%) ✅

Breakdown Analysis:

Cost Component          Estimate    Actual    Variance
Baseline eCKU          $2,800      $2,800    0%
Auto-scaling           $400        $480      +20%
Storage                $10         $12       +20%
Networking             $150        $140      -7%
──────────────────────────────────────────────────
Total                  $3,360      $3,432    +2% ✅

If Costs Higher than Expected: - Investigate auto-scaling frequency - Review storage growth - Check networking patterns - Compare to Dedicated (still saving?)

## Step 6.4: Performance Validation

### Benchmark Comparison

Latency Comparison:

Dedicated (before):
- p50 latency: 12ms
- p95 latency: 25ms
- p99 latency: 45ms

Enterprise (after):
- p50 latency: 11ms ✅
- p95 latency: 23ms ✅
- p99 latency: 42ms ✅

Result: Performance maintained or improved

Throughput Comparison:

Dedicated: 30 MB/sec average, 90 MB/sec peak
Enterprise: 30 MB/sec average, 92 MB/sec peak

Result: Throughput unchanged ✅

Load Testing (Optional but Recommended):

# Simulate peak load
kafka-producer-perf-test \
  --topic load-test \
  --num-records 1000000 \
  --throughput 50000 \
  --record-size 1024 \
  --producer-props bootstrap.servers=<enterprise>

Result: 
- Enterprise handled peak without issues ✅
- Auto-scaled appropriately ✅
- Latency remained stable ✅

## Step 6.5: Stakeholder Validation

### Business Confirmation

Weekly Check-ins:

Week 1: 
✅ Engineering: No issues reported
✅ Product: Metrics look normal
✅ Finance: Costs tracking to estimate

Week 2:
✅ Engineering: One minor issue (resolved)
✅ Product: All features working
✅ Finance: Savings confirmed

Week 3-4:
✅ All teams: Confident in stability
✅ Ready to proceed with decommission

Formal Sign-Off:

Stakeholder Approval Checklist:
- [ ] Engineering Lead: Approves technical stability
- [ ] Product Manager: Confirms business metrics
- [ ] Finance: Validates cost savings
- [ ] Security: Confirms compliance maintained
- [ ] Executive Sponsor: Authorizes Dedicated cleanup

## Validation Period Durations

### How Long to Validate

1 Week Validation: - Non-production environments - Low-risk workloads - Aggressive timeline

2-3 Weeks Validation (Recommended): - Production environments - Standard risk tolerance - Covers multiple weekly cycles

4+ Weeks Validation: - Mission-critical systems - Conservative approach - Covers monthly processes (month-end, quarter-end) - Regulated industries

Our Recommendation:

Non-Prod: 1 week
Production: 3 weeks minimum
Critical: 4-6 weeks

## Step 6 Deliverables

### Validation Complete

Metrics Reports: - Daily monitoring dashboards - Weekly cost reports - Performance comparison analysis - Auto-scaling behavior summary

Issue Tracking: - Issues encountered log - Resolutions implemented - Outstanding items (if any)

Stakeholder Approval: - Sign-off from all stakeholders - Authorization to decommission Dedicated - Documentation of validation period

Readiness: - Enterprise validated as stable production cluster - Dedicated ready for decommission - Team confident in migration success

## STEP 7: Decommission Dedicated

### Week 11+ (1 day)

## Step 7.1: Pre-Decommission Checklist

### Final Verifications

Before You Delete Dedicated:

- Enterprise running stably for 2-4+ weeks

- All applications migrated (Dedicated traffic = 0)

- All validation checks passed

- Stakeholder approval received

- Backup of configurations (optional paranoia)

- Rollback plan understood (can’t rollback after deletion)

- Team ready to monitor Enterprise closely post-cleanup

Check Dedicated Traffic:

# Verify Dedicated has zero traffic
confluent kafka cluster describe <dedicated-cluster-id>

# Check metrics in UI
Dedicated Cluster → Metrics → Throughput
Should show: Ingress = 0, Egress = 0

If ANY traffic on Dedicated → STOP! Investigate before deleting!

## Step 7.2: Delete Cluster Link

### Remove Synchronization

Why Delete Link First: - Cluster Link itself costs money - No longer needed (Enterprise is independent) - Clean separation before deleting Dedicated

How to Delete:

confluent kafka link delete dedicated-to-enterprise \
  --cluster <enterprise-cluster-id>

Expected Result: - Link removed - Mirror topics on Enterprise remain (but are now independent) - No more sync from Dedicated

Verify:

confluent kafka link list --cluster <enterprise-cluster-id>
# Should show: No cluster links found

## Step 7.3: Delete Dedicated Cluster

### The Final Step

Via Confluent Cloud UI:

- Navigate to Dedicated Cluster

- Go to Settings → Scroll to bottom

- Click “Delete cluster”

- Type cluster name to confirm: dedicated-prod

- Click “Delete”

- Confirmation: “Cluster deletion initiated”

Deletion Timeline: - Processing: 15-30 minutes - Email notification when complete - Billing stops immediately

## Delete Dedicated (CLI Method)

### Command-Line Approach

Delete Cluster:

confluent kafka cluster delete <dedicated-cluster-id> --force

Expected Output:

Cluster "lkc-xxxxx" scheduled for deletion.
This operation cannot be undone.

Verify Deletion:

confluent kafka cluster list

# Dedicated cluster should not appear in list

Monitor Deletion Status:

Confluent Cloud UI → Environments
Status: "Deleting..." → "Deleted"

## Step 7.4: Clean Up Networking

### Remove Old Connections

Delete VPC Peering (if no longer needed):

# AWS example
aws ec2 delete-vpc-peering-connection \
  --vpc-peering-connection-id pcx-xxxxx

Delete Transit Gateway Attachments:

aws ec2 delete-transit-gateway-vpc-attachment \
  --transit-gateway-attachment-id tgw-attach-xxxxx

Remove DNS Entries:

# Delete Route 53 records for Dedicated endpoints
aws route53 change-resource-record-sets \
  --hosted-zone-id Z123456 \
  --change-batch '{ "Changes": [...]}'

Clean Up Security Groups (Optional):

# Remove rules specific to Dedicated cluster
aws ec2 revoke-security-group-ingress \
  --group-id sg-xxxxx \
  --ip-permissions ...

## Step 7.5: Update Documentation

### Final Housekeeping

Update Architecture Diagrams: - Remove Dedicated cluster - Show only Enterprise cluster - Update network flow diagrams

Update Runbooks: - Application connection details (Enterprise endpoints) - Monitoring procedures (Enterprise cluster) - Incident response playbooks

Update Configuration Management: - Remove Dedicated configs from Git - Archive old Terraform code - Update CI/CD pipelines

Update Knowledge Base: - Migration retrospective - Lessons learned - Best practices for future migrations

## Step 7.6: Verify Cost Savings

### Confirm Billing Changes

Next Month’s Bill:

Previous Month (Overlap Period):
- Dedicated: $4,500
- Enterprise: $3,360
- Total: $7,860 ❌

Current Month (Post-Migration):
- Dedicated: $0 ✅
- Enterprise: $3,360 ✅
- Total: $3,360 ✅

Monthly Savings: $1,140 (25%)
Annual Savings: $13,680

Review Invoice:

Confluent Cloud UI → Billing → Invoices
- Verify Dedicated charges stopped
- Verify Enterprise charges match estimate
- Confirm savings realized

## Step 7.7: Celebrate Success! 🎉

### Migration Complete!

What You Achieved:

✅ Zero-downtime migration - No service interruption
✅ Zero data loss - All data migrated successfully
✅ Cost savings - 20-60% monthly savings realized
✅ Auto-scaling - No more manual capacity management
✅ Modern platform - On Confluent’s strategic platform
✅ Team learning - Built migration expertise

Share Success: - Announce to organization - Thank migration team and stakeholders - Document case study - Share lessons learned with peers

Next Steps: - Monitor Enterprise ongoing - Optimize costs as needed - Plan future migrations (dev/test environments?) - Enjoy the savings! 💰

## Step 7 Deliverables

### Final Documentation

Completion Report: - Migration timeline (actual vs. planned) - Cost savings achieved (actual vs. estimated) - Issues encountered and resolutions - Lessons learned and recommendations

Updated Assets: - Architecture diagrams (Enterprise only) - Runbooks and procedures - Configuration management (Git, Terraform) - Knowledge base articles

Stakeholder Communication: - Success announcement - Cost savings report - Future optimization opportunities

Cleanup Confirmation: - Dedicated cluster deleted ✅ - Networking cleaned up ✅ - Billing verified ✅

## Timeline Summary

### Complete Migration Journey

Week-by-Week Breakdown:

| Week | Activity | Status |
| --- | --- | --- |
| 1-2 | Discovery & sizing | Dedicated runs normally |
| 2 | Provision Enterprise | Both clusters exist |
| 2-3 | Cluster Linking | Enterprise syncing |
| 3 | Pilot migration | Small traffic on Enterprise |
| 3-6 | Full migration | Most traffic on Enterprise |
| 6-11 | Validation | Enterprise is primary |
| 11+ | Decommission | Enterprise only ✅ |

Total Duration: 4-11 weeks (depends on complexity and risk tolerance)

## Resource Requirements

### Team and Skills Needed

Core Migration Team (Recommended): - 1 Project Manager (planning, coordination, tracking) - 2-3 Engineers (Kafka expertise, hands-on migration) - 1 Network Engineer (Private Link setup, DNS) - 1 DevOps Engineer (CI/CD, automation)

Part-Time Contributors: - Application owners (config updates per app) - Security team (compliance review, approvals) - Finance team (cost tracking, approvals)

Time Commitment:

Project Manager: Full-time (8-12 weeks)
Engineers: 50-75% time (6-8 weeks)
Network Engineer: 25% time (2-3 weeks)
DevOps: 25% time (ongoing support)
App Owners: 10-20 hours each (1-2 weeks)

## Skills Required

### Technical Competencies

Must Have: - ✅ Kafka fundamentals (topics, producers, consumers) - ✅ Confluent Cloud console familiarity - ✅ Basic networking (VPCs, DNS, Private Link) - ✅ Application configuration management

Nice to Have: - ✅ Terraform (for infrastructure-as-code) - ✅ Kubernetes (if containerized apps) - ✅ Monitoring tools (Prometheus, Grafana, Datadog) - ✅ Scripting (Bash, Python for automation)

Can Learn During Migration: - Cluster Linking (new to most teams) - Enterprise cluster specifics - Private Link networking model - Auto-scaling behavior

Confluent Support Available: - Professional Services (hands-on help) - Technical Account Manager (guidance) - Support tickets (troubleshooting) - Documentation and training

## Risk Mitigation

### How We Reduce Risk

Technical Risks:

Risk: Data loss during migration
Mitigation: - ✅ Cluster Linking preserves all data - ✅ Dedicated keeps running as source of truth - ✅ Verify lag = 0 before cutover

Risk: Application connectivity failures
Mitigation: - ✅ Pilot migration validates process - ✅ Test connectivity before migrating apps - ✅ Rollback procedure documented and tested

Risk: Performance degradation
Mitigation: - ✅ Size Enterprise appropriately - ✅ Load testing before production cutover - ✅ Monitor performance closely during migration

## Risk Mitigation (Continued)

### More Risk Controls

Business Risks:

Risk: Extended downtime impacts revenue
Mitigation: - ✅ Zero-downtime migration strategy - ✅ Phased migration (can pause if needed) - ✅ Dedicated available for immediate rollback

Risk: Higher costs than expected
Mitigation: - ✅ Detailed cost estimate upfront - ✅ Monitor costs during overlap period - ✅ Can rollback if costs unfavorable

Risk: Missed business-critical processes
Mitigation: - ✅ Validate for full business cycle (month-end, quarter-end) - ✅ Stakeholder review before decommission - ✅ Keep Dedicated 2-4+ weeks for safety

## Rollback Strategy

### When and How to Rollback

Rollback Scenarios: - ❌ Enterprise performance issues - ❌ Critical application failures - ❌ Data inconsistencies detected - ❌ Network connectivity problems - ❌ Costs significantly higher than expected

Rollback Procedures by Stage:

Before Topic Promotion (Easy - Minutes):

1. Stop apps on Enterprise
2. Revert config to Dedicated endpoints
3. Restart apps on Dedicated
✅ Data safe (Dedicated has everything)

After Topic Promotion (Moderate - Hours):

1. Create reverse Cluster Link (Enterprise → Dedicated)
2. Wait for sync
3. Promote topics on Dedicated
4. Point apps back to Dedicated
⚠️ Requires coordination, takes longer

## Rollback (Continued)

### Point of No Return

After Dedicated Deleted (Cannot Rollback):

❌ Dedicated is gone
❌ Can't go back to old cluster
✅ Must fix forward on Enterprise

Options if issues arise:
1. Troubleshoot and fix on Enterprise
2. Create new Dedicated if absolutely necessary (expensive, slow)

Best Practice: - Don’t delete Dedicated until 100% confident - Cost of keeping Dedicated 2-4 extra weeks is small - Insurance against costly mistakes

Decision Framework:

Can rollback? → Keep Dedicated
Cannot rollback? → Delete Dedicated only when certain

## Success Criteria

### How to Measure Success

Technical Success: - ✅ Zero unplanned downtime - ✅ Zero data loss - ✅ All applications migrated - ✅ Performance maintained or improved - ✅ Auto-scaling working correctly

Business Success: - ✅ Cost savings achieved (target: 20-60%) - ✅ Business metrics unchanged - ✅ Stakeholder satisfaction - ✅ No customer impact

Operational Success: - ✅ Team learned migration process - ✅ Documentation complete - ✅ Repeatable for other environments - ✅ Reduced operational overhead (auto-scaling)

## Lessons Learned Template

### Post-Migration Review

What Went Well: - Cluster Linking worked perfectly - Pilot migration caught configuration issues early - Team coordination was excellent - Stakeholders well-informed

What Could Be Improved: - DNS setup took longer than expected - More automation needed for config updates - Need better monitoring during migration

Recommendations for Next Time: - Start with better networking documentation - Build config templates earlier - Allocate more time for validation

Metrics: - Planned: 8 weeks | Actual: 9 weeks - Estimated savings: 25% | Actual: 28% - Issues: 3 minor | Downtime: 0 minutes

## Next Steps After Migration

### Optimization Opportunities

Cost Optimization: - Review eCKU baseline (right-sized?) - Optimize topic retention policies - Clean up unused topics - Leverage PNI for networking savings (AWS)

Performance Optimization: - Tune producer/consumer configurations - Review partition strategies - Optimize Schema Registry usage - Implement data compaction where appropriate

Operational Improvements: - Set up advanced monitoring dashboards - Create alerts for anomalies - Document troubleshooting runbooks - Train team on Enterprise features

Future Migrations: - Apply learnings to dev/test environments - Migrate other Dedicated clusters - Evangelize success to other teams

## Appendix: Key Contacts

### Who to Contact for Help

Confluent Support: - Support tickets: Confluent Cloud UI → Support - P1 (Critical): <1 hour response - P2 (High): <4 hours response

Your Confluent Team: - Account Manager: [Name, Email] - Solutions Architect: [Name, Email] - Technical Account Manager: [Name, Email] (if applicable)

Internal Team: - Project Manager: [Name] - Lead Engineer: [Name] - Network Team: [Contact] - Security Team: [Contact]

Emergency Contacts: - On-call rotation: [Phone, Slack] - Escalation path: [Process]

## Appendix: Useful Commands

### Quick Reference

Check Cluster Info:

confluent kafka cluster describe <cluster-id>

Monitor Consumer Lag:

confluent kafka consumer group describe <group> \
  --cluster <cluster-id>

Check Cluster Link Status:

confluent kafka link describe <link-name> \
  --cluster <cluster-id>

List Mirror Topics:

confluent kafka mirror list \
  --cluster <cluster-id> \
  --link <link-name>

Promote Mirror Topic:

confluent kafka mirror promote <topic> \
  --cluster <cluster-id> \
  --link <link-name>

## Appendix: Terraform Examples

### Sample Code

Enterprise Cluster:

resource "confluent_kafka_cluster" "enterprise" {
  display_name = "enterprise-prod"
  availability = "MULTI_ZONE"
  cloud        = "AWS"
  region       = "us-east-1"
  
  enterprise {
    ecku = 2
  }
  
  environment {
    id = confluent_environment.prod.id
  }
}

Cluster Link:

resource "confluent_cluster_link" "main" {
  link_name = "dedicated-to-enterprise"
  
  source_kafka_cluster {
    id = var.dedicated_cluster_id
    credentials {
      key    = var.dedicated_api_key
      secret = var.dedicated_api_secret
    }
  }
  
  destination_kafka_cluster {
    id = confluent_kafka_cluster.enterprise.id
  }
  
  config = {
    "consumer.offset.sync.enable" = "true"
  }
}

## Q&A

### Questions?

Common Questions:

- How long does the migration take?

- Is there any downtime?

- What if something goes wrong?

- How much will we save?

- Do we need Confluent help?

Contact Information: - Email: [your-email@company.com] - Slack: #kafka-migration - Office Hours: Tuesdays 2-3 PM

## Thank You!

### Migration Success Awaits

Key Takeaways: - ✅ Zero-downtime migration is possible - ✅ Cluster Linking is the enabling technology - ✅ Pilot testing reduces risk - ✅ Phased approach is safest - ✅ Savings typically 20-60%

Next Steps: 1. Review this presentation with your team 2. Schedule discovery session 3. Build business case 4. Get stakeholder buy-in 5. Plan migration timeline

Let’s get started! 🚀

END OF PRESENTATION

Document Version: 1.0
Last Updated: April 21, 2026
Prepared by: [Your Name]
For: Confluent Dedicated to Enterprise Migration